## README
Last Update | 2019-04-22
Author | Melvin Su / Kaitlyn Shih / Jeff Trang / Kevin Frazier
Email | msu009@ucr.edu / kshih007@ucr.edu / jtran094@ucr.edu / kfraz001@ucr.edu
Description | Team: untitled
Summary / Requirements | This spreadsheet serves two purposes: (1) for your team to track progress during your sprints, and (2) as a record of what user stories were implemented, in which tasks, and by whom. For (1), if you prefer to use an alternate tool to track progress as you go (e.g., Trello), that is fine. However, for (2), it is critical that you keep the "Product Backlog" and "Archives" up to date, at least at the end of each sprint. Also, note that if the number of estimated points for a story ends up being very inaccurate (i.e., if the user story took much more or much less effort than expected), please update the story points estimate and give a comment explaining the adjustment.
Tabs | Notes
"Product Backlog" | Should be initialized with the user stories and their estimated efforts (i.e., story points)
Depending on the amount of story points, some stories may need to be split into smaller stories
Add "Acceptance Criteria" to each user story by "insert note" to a spreadsheet cell (right click the cell)
"Acceptance Criteria" define what it means to be "Done"
"Task Board" | "To Do" is initialized with tasks defined during the Sprint Planning Meeting (i.e., sprint backlog)
Tasks are expected to have similar sizes, each with a time cost of roughly 3-4 hours
Add "Details" and "Acceptance Criteria" to a task by "insert note" to a spreadsheet cell (right click the cell)
Perform task assignments at the Sprint Planning Meeting
During a sprint, members who become available can pull tasks from the "To Do" list by moving them to "In Progress" and attaching his/her name
Inform your teammates know before you pull a task from "To Do" list
"To Verify" should be pulled by a different team member; This is a good time to perform code review and unit testing
A task in "Done" list should have its verifier's name appended
"Archives" | At the end of a Sprint, finished tasks are moved to "Archives"; Unfinished tasks are moved to the next Sprint Planning Meeting
"Burndown Chart" | At the end of a Sprint, update the "Burndown Chart"
if "Story Points (Remaining)" is above the "Ideal", it would be an indicator for slow progress

## Product Backlog
ID | Story Name | Story (small features) | Story Points | Priority | Comments
| Profile Creation | As a customer, I want to be able to create a profile with an authenticated password | 5 | 1 | - needs database backend to store each user
| Group Creation | As a registered user, I can create a specific group with its own page | 6 | 2 | -need to keep track of whos in each group
| Create Event | As a group member, I should be able to create events under that group that group members can see and join | 6 | 3 | -need to track what event belongs to each group
| Join Group | As a registered user, I should be able to join as many as I want | 4 | 4
| Join Event | As a group member, I can join any event within my group. | 4 | 5
| Search for Events | As a user, I should be able to search for events based on their name | 8 | 6
| Messaging | I can message anyone from group | 9 | 7
| Profile Editing | As a registered user, I want to edit/update my profile information | 2 | 8
| Edit Event | As an event creator, I should be able to see who is attending the event | 2 | 9
| Total |  | 46

## Task Board
Trello Link | To Do (Sprint Backlog) | In Progress | Testing | Done
https://trello.com/b/TfoSSSRy/task-board | (Profile Creation) Group Feed | High Priority: | (Event Creation) Event Details | (Group Creation) Create Database
|  | Profile, Group, Login, Authenticate User |  | (Event Creation) Create Database
|  | Profile, Group, Login - Check input format | (Group Creation) Group Details | (Profile Creation) Login Page
|  | Profile,Group, - Update those Pages with correct credentials |  | (Profile Creation) Profile Page
| (Event Editing) Add/Delete Group Member | Profile, Group Event - Edit Information/Update the Database |  | (Profile Creation) Create Database/add User to Database
| (Event Editing) Update Information | Group,Event - Join
| (Join) Update Event's Join List | Low Priority:
| (Join) Update Group's Join List | (Profile Editing) Add/Delete Groups
(Search) Create Search Bar
(Search) Search for Groups/Events
(Search) Show Event Results
(Group Threads) Store Posts and Time Stamps
(Group Threads) Show Posts and Time Stamp
(Group Threads) Edit Post
(Group Threads) Add/Delete Message
(Join Group) Add User to Group Database

## Archives
Sprint ID | Scrum Master | Tasks Completed
0 | Kevin Frazier | Profile Creation - add to Database
Group Creation - add to Database
Event Creation - add to Database
1 |  | Page Templates
2
3
4
5
6
7
8

## Burndown Chart
Sprint ID | Story Points (Total) | Story Points (Completed) | Story Points (Accumulated) | Story Points (Remaining) | Ideal
0 | 46 | 0 | 0 | 44 | 35
1 | 46 | 0 | 0 | 44 | 30.625
2 | 46 | 0 | 0 | 44 | 26.25
3 | 46 | 0 | 0 | 44 | 21.875
4 | 46 | 0 | 0 | 44 | 17.5
5 | 46 | 0 | 0 | 44 | 13.125
6 | 46 | 0 | 0 | 44 | 8.75
7 | 46 | 0 | 0 | 44 | 4.375
8 | 46 | 0 | 0 | 44 | 0